EVENTLY

Launch Plan — Web Prototype to App Store + Play Store

From validated prototype to soft launch in your first metro  ·  v1.0  ·  May 2026

# Reality check before committing

The web prototype is roughly 15% of the work to launch. It is a Figma replacement that runs. To ship to the App Store and Play Store, the app must become a real native application with a real backend, real payments, and trust-and-safety operations behind it.

Two paths to a store-shippable app:

- Expo (React Native) — recommended by the PRD and by me. Single codebase iOS + Android, OTA updates, professional ceiling. Maps cleanly from the existing web UX.

- Capacitor wrap — shells the web app in a native container. Ships 2–3 months faster but ceiling is lower and Apple occasionally rejects web-only apps.

This plan assumes Expo. If timeline forces Capacitor, the phases stay the same; only the client work shrinks.

# The phased plan

Seven phases, six to nine months total for a solo developer or four to five months for a small team. Each phase ends with a shipped milestone, not an internal demo.

| Phase | Timeline | Key work |
| --- | --- | --- |
| Phase 0 | Week 0 (3–5 days) | Decisions — platform (Expo vs Capacitor), launch metro, brand domain Accounts — Apple Developer ($99/yr), Google Play ($25 one-time), Stripe Connect application (1–2 wk approval) Vendors — Twilio Verify for SMS, Supabase project, Sentry, PostHog Legal — engage marketplace lawyer for TOS / Privacy / Vendor Agreement review (~2–3 wk) |
| Phase 1 | Weeks 1–4 | Backend — Supabase schema from PRD §12.2, Row-Level Security, soft-deletes, idempotent webhooks Auth — phone OTP via Twilio + Sign in with Apple + Google Sign-In Mobile shell — Expo project, EAS Build → TestFlight + Play Internal Testing Design system port — Tailwind/CSS → React Native StyleSheet (or NativeWind) |
| Phase 2 | Weeks 5–14 | Vendor app — profile, packages, real calendar, Instagram OAuth, Google Places reviews Payments — Stripe Connect Express account, KYC, payout schedule Admin — Retool dashboard for vendor approvals + manual edits Beta — 20–30 hand-recruited vendors using it as a free calendar Milestone — 20 vendors maintain calendar weekly for 4 weeks straight |
| Phase 3 | Weeks 15–24 | Customer app — port event wizard, real discovery with PostGIS, filters Booking — inquiry → 24h hold → vendor accept → Stripe split charge Messaging — Supabase Realtime + contact-info masking Day-of — event dashboard, timeline, vendor list Push — Expo Push Notifications wired to APNS/FCM Milestone — 50 confirmed bookings end-to-end |
| Phase 4 | Weeks 25–32 | Trust & safety — dispute flow, refund automation, content moderation, vendor verification Quality — crash-free >99.5%, p95 screen <1.5s, accessibility audit (WCAG 2.1 AA / AODA) Privacy — PIPEDA data export + delete flows, privacy review Store assets — screenshots, video previews, app icon, splash, demo account for reviewers Submission docs — Apple Privacy Nutrition + Google Data Safety forms |
| Phase 5 | Weeks 33–36 | Internal beta — TestFlight + Play Internal — 1 week shake-out External beta — 100 invited users in launch metro — 1–2 weeks Store review — Apple 5–7 days, Google 1–3 days, plan for resubmissions Soft launch — launch metro only; 2% facilitation fee for first 500 customers |
| Phase 6 | Weeks 37+ | Operations — support inbox (Intercom or Help Scout), payout reconciliation, dispute SLA Growth loops — customer referrals ($25 credit), vendor referrals (1 mo Pro free), SEO landing pages Second metro — after $25K MRR or 200 confirmed bookings/month |

# Cost envelope

Conservative estimate for a one-metro Canadian launch. Excludes paid marketing, which scales separately based on funding.

| Item | One-time | Recurring |
| --- | --- | --- |
| Apple Developer Program | — | $99/year |
| Google Play Developer | $25 | — |
| Domain (evently.app / .com) | $15–60 | $15–60/year |
| Marketplace lawyer (TOS / Privacy) | $2,500–6,000 | annual review ~$1,000 |
| Supabase (free tier → Pro) | — | $0 → $25/month from beta |
| Twilio Verify SMS | — | $0.05/verification (~$50–200/mo at beta) |
| Sentry + PostHog | — | free tier sufficient until ~5K users |
| Stripe processing | — | 2.9% + 30¢ per charge (passed through) |
| Marketplace E&O insurance | — | $2,000–5,000/year |
| Contract React Native dev (if solo) | — | $60–120/hr · roughly 400–600 hours |
| Designer for store screenshots | $800–2,500 | — |
| Total budget estimate | $3,500–11,000 | $3,500–8,000/year + dev hours |

# Risk register

Read this before committing time or money.

| Risk | Why it bites | Mitigation |
| --- | --- | --- |
| Apple review rejection | Marketplaces with in-app payments get extra scrutiny | Stripe Connect (not IAP), demo account, Sign in with Apple, sample data |
| Cold-start failure | Empty marketplace kills the app on day one | Hand-recruit 50–80 vendors before opening to customers |
| Vendor circumvention | Take rate erodes if leakage is high | Layered defenses per PRD §10 + on-platform tools more useful than off-platform |
| Legal / compliance gaps | Marketplace TOS, tax, insurance can blow up post-launch | Lawyer review before submission; marketplace E&O insurance |
| Solo bandwidth | 6–9 months full-time for one person | Outsource design system + admin via Retool; hire contract iOS/Android polishing pre-launch |
| Stripe Connect approval delay | Can take 1–2 weeks; blocks payments work | Apply during Phase 0 in parallel with prototype work |
| Sign-in-with-Apple omission | Mandatory if any other social login exists | Build in Phase 1, not Phase 4 |
| App Store reviewer can't see what app does | Most common rejection reason for marketplaces | Maintain a permanent sample reviewer account with seeded data |

# The three things to do this week

Before committing to the full native port, three steps move the needle and de-risk the bigger plan:

- Add the missing demo screens — dispute flow, review prompt, day-of timeline, multi-vendor checkout. Tells the complete story in the prototype. ~1 week.

- Deploy the prototype publicly — Vercel or Netlify gives a shareable URL. ~1 day.

- Start vendor outreach — the working prototype is the pitch. Aim for 10 verbal “I'd use this” commitments before writing a line of React Native code.

Concrete decision rule: if 10 vendors say they would use it, commit to Phase 1. If fewer than 5 do, the product is not yet right and the prototype needs revisions before any native build.

# Hand-off — what your developer needs from you

When you bring on a developer, give them this in writing:

- This document plus the PRD and the Positioning + Roadmap doc. Three documents = one complete brief.

- Access to the prototype repo, the Figma file (or current designs), and any brand assets.

- Access to all third-party accounts (Apple, Google, Stripe, Supabase, Twilio, Sentry, PostHog) with appropriate roles.

- A definition of done for Phase 1 — vendor can sign up, complete Stripe Connect onboarding, create a profile, and block dates on their calendar.

- A budget and timeline expectation — Phase 1 is 4 weeks for a senior React Native developer. Anything faster is a red flag; anything slower than 6 weeks needs investigation.

- A weekly check-in cadence — Friday demo of what shipped that week. No demo = no progress.

# North Star and what to watch

Booked Events per Month (BEPM) — events where the customer confirmed two or more vendors through Evently in the same calendar month.

Everything else — GMV, MRR, NPS, MAU — is downstream of BEPM. Lock this single metric and report on it weekly from the day the first booking lands.

# Final note

This plan is conservative. With a great developer and a tight scope, Phases 1–3 can compress. With slower than expected vendor recruiting, Phase 2 extends. The phases are the right shape regardless of who is doing the work — they sequence by what unlocks customer value first.

—  Find, compare, and book. Every event, one app.  —